## Sheet1
Date | Time | Hours | Objective
2023-08-28 | 9am-10am | 1 | Finding a group and getting the contact information.
2023-08-29 | 9am-2pm | 4 | Borrowed a C# fundamental textbook and watched youtube videos about unity. Download Unity
2023-08-30 | 9am-2pm,10pm-11pm | 6 | Read the Unity manual guide, play the tutorial LEGO game, and chat group meeting.
2023-08-31 | 9am-12pm,2pm-4pm | 5 | Learning from the tutorial LEGO game and Completing the project proposal.
2023-09-01 | 9am-7pm | 10 | Reading 50 pages from HeadFirst C#(learner guide), learn about XAML and C# coding in VS.
2023-09-02 | 9am-11am | 2 | Read online sources about design document, project lifecycle,project management board.
2023-09-04 | 9am-2pm | 5 | Watch Build your first 3D Game in unity by Coding in flow.
2023-09-05 | 9am-2pm | 5 | Read Unity manual documentation:Introduction to 2D
2023-09-06 | 3pm-4pm | 1 | Meeting with the project Supervisor to discuss ideas about the project and project design.
2023-09-07 | 9am-1pm | 4 | Reading how to create a design document and writing the first draft design document.
2023-09-08 | 9am-11am | 2 | Reading Learn C# programming from tutorialspoint.
2023-09-11 | 2pm-3:30pm | 1.5 | Group meeting to create and change the final design document.
2023-09-12 | 9am-11:30am | 2.5 | Reading the unity manual document about the components and triggers.
2023-09-13 | 10am-2pm | 4 | Watch C# tutorial Helicoper 3D-CS50's intro to Game development from freecodeacademy